## Sheet1
# | Risk | Probability | Consequence | Mitigation Steps | Probability after mitigation | Consequence after mitigation | Status | Writeup
1 | MeOAc-MeOH Azeotrope | 10% | Impure Product | Run Distillation Column at Correct Pressure | <10% | Accept added costs from a higher pressure being used, Pure Product |  | Adarsh
2 | Large of Carbon Monoxide is Purged | 50% | Profit Loss | Add more Hydrogen gas into reactor to create more methane gas | 25% | Added costs of Hydrogen gas being added, acceptable purge of carbon monoxide and methane |  | Adarsh
3 | High Pressure In Dehydration Reactor (25 bar) Leading to explosion | <5% | Critical failure of reactor | Add safety valves to release pressure if needed as well as adding alarm moniters for increasing pressure in reactor | <1% | Added costs from pressure reliefs valves, safer/ more stable reactor system |  | Gavin
4 | High Peak temperature in either reactor leading to catalyst degradation | 10% | Decreased yield of product | Cooling Liquids with constant flow through reactor jackets regulate temperature rise | <1% | costs from utility usage (high pressure steam/Dowtherm), more stable catalyst
5 | Carbon monoixde in last distilation column feed | 25% | possible required cryogenics for distillation (High Cost) | Use Partial condensor to allow for easier seperation | <10% | Decreased costs compared to cryogenics
6 | Exothermic Reaction leading to explosion |  | Critical Failure of reactor and plant
7 | High Pressure Fired Heater |  | Critical failure of heat exchanger
8 | Possible Plant Leak |  | Loss of material which could lead to other hazards |  |  |  |  | Gavin
Power Failure
Excessive Vibration of Flash tank
| Large Pressure Changes |  | Critical Failure
| Pressure buildup in flash tanks |  | Critical Failure
| Methanol Poisoning (Water Contamination) |  | Health issues, blindness, death, carcinogen?? |  |  |  |  | Gavin
| Effect of purging methane and carbon monoxide | 100% | [5 empty] | Adarsh
| Waste Stream of Methanol | 100% | Health issues part 2 unless we can find a treatment methodology?
| Effect of feeding hydrogen gas (Combustion) | 100% | Explosion due to violent combustion or depressurization |  |  |  |  | Adarsh
| DME(just in general related to safety) |  | Flammable,but we have low quantities in product and waste streams
High/Low Pipe Temperatures